## Phase_1_Development
ProPad (Phase 1) - iOS App Design & Development
Technology: iOS SDK, X Code, Objective C
Date: 24th June, 2015
Module | Task | iOS Development
|  | Time [Hrs.] | Resource
Application Design & Integration
App Design | App Logo Design | 16 | App Designer
Main Page Mock up Design
Main Page modifications & finalization
Inner Pages Design
Design Integration | Design Slicing | 10 | iOS Developer
Integration to iOS Framework
Application Development (Project Scope)
Splash Page | App Logo Show App logo with background Image. | 2 | iOS Developer
Keep Splash page stayed for some time while loading an app and then take user to Login Page.
User Login | User Login with Username/Password Take User to Dashboard upon successful login. | 4
Remember Me This will remember username only and not remember PIN.
Reset Password
User Register | New Users need to fill in the required information and get registered on App. Information would be | 8
- First Name - Last Name - Email Address (Username) - PIN - Confirm PIN
- Company Code (It will populate company name upon entering code) - New/ Used Vehicle Salesperson (Radio or checkbox) and submit details.
Upon submit Check Validations. Moreover, It will verify company code with DB and get user registered on app.
Dashboard | Show Company Name & Logo | 8
Menu Implementation
Menu Items would be - Client List - New Client - Coming Soon - it will show content page.
Client Module | List down Clients added | 18
Search Clients by First Name, Last Name
Search Clients by Vehicle of Interest (Make/ Model/ Year)
Sort Clients by Date/Month
Client listings - each client would display - Customer Name - Vehicle of Interest - Date of Visit Click on any and it will take user to client detail page.
Highlight SOLD Clients with Yellow color and LOST Clients with Red Color
| Client details - it shows - Sections 1, 2 & 3 details as user has filled out | 16
Show following info -Front Gross (Number Field) -Back Gross (Number Filed) -Total Gross on deal (Total of Front & Back Gross Fields)
Show Time Stamp of Add and Last Edit
| Ability to Edit/ Update Client Info User can click on edit and it will allow user to edit & update customer details. | 10
Add New Client | This will allow user to add new customer. This will represent different sections and ask user to fill in accordingly. | 16
Section 1 (Customer Info) - Customer Type (1st Time Customer / Be Back / Previous Customer / Appointment) - How did you hear about us? (Internet / Walk In / Referral / Mailer / 3rd Party Website / Other)
- First Name - Last Name - Address - City - State - Zip - Mobile# - Home# - Work#
- Email Address - Preferred Contact Type (Checkbox - Phone/Email/Text) - Notes Field
| Section 2 (Customer Current Vehicle) - Enter Make/Model/Year manually | 8
- Current Miles on Vehicle (Number Field)
Questions -What is your Current Monthly Payment?(Number Field) After user enters number a popup should display with 4 buttons in this order top to bottom(100-200 / 50-100 / Same / Lower) when user selects one of these it should populate beneath the current payment number field. Header on popup should read “Desired Monthly Payment”. -What is your desired Monthly Payment? (Number Field) -Notes (Text Field)
| Section 3 (Vehicle of Interest) - Primary Choice Make/ Model/ Year and Stock# - Secondary Choice Make/ Model/ Year and Stock# | 10
| and submit details | 8
Upon submit It will save data into local device memory. And send this email info to email addresses defined through back end.
Send Email Configuration & Integration
Note: Client details would not be saved on Server DB.
Project Management Final Testing and Deployment
Project Management | Review Project Documents & Understand Project Scope; Resources allocation | 6 | PM
Project kick off meeting with the Team & Client; Writing and distributing meeting minutes; Solving Queries from the Client and Developer
Project Progress Updates and Demos to Client and overall Project Management
Testing & Deployment | Executive a compatibility test matrix | 8 | Quality Tester
Functional testing of features with proper validations
User Acceptance and Performance Testing
Test under low memory conditions, Accurately report available memory
Usability testing: Test for navigation, Content checking
Total Hours |  | 148
Back End and Web Services |  |  | PHP Developer
Admin Sign in | Sign in with Username/ Password | 14
Change Password
Companies | View Companies added
Edit/ Update Company Details
Add New Company Admin needs to enter required details and add company to DB. Details would be Company Name, Code, Upload Logo image and Associated Email Addresses.
Users | View Users registered | 6
Sort Users by Company
Edit/ Update User's details
Add new User
Web Services | Web Services Development | 18
Total Hours |  | 38
Notes
iOS application will use Portrait layout throughout the execution.
IPhone application will support iPod Touch (4th & 5th Generation), iPhone 4S, iPhone 5/5S/5C/6/6+ as well as iPad 2, the new iPad & iPad mini with OS versions 8.x.
This estimation is based on above explained features which is subject to change based on any change in features/functionality while in actual implementation.