## B95-Phase2
IOS PROJECTS
Project Name: B95 Phase 2
Current Developer: Aakil
Sr. No | Modules | Tasks Details | Estimates | QA
1 | In App Purchase | Only Premium Member (IAP) or Serial number users can get all features of app. It was already done in Phase 1, but now it's not working, so need to double check.
2 | Line Up and Poll | Players Pictures are not dispalying properly. Make sure both modules workd properly.
3 | Social Network | Post predefined messages at the social network are not working.
4 | Route | It's not working properly. Please make some improvements in layout and also make sure Change location would work properly.
5 | Performance Issues | Applicationneed to load smoothly in Social Networking, Route, and Weather. Please make sure everything work smoothely in 3G as well.
6 | Music File | Need to check Memory leaks and other memory issues.
7 | Game: Quiz Section | Notification are not working properly
8 | Localization (Multiple Languages) | Need to put updated contents of all languages, and it should load properly, same like English language.
9 | Exception Handling | Need to do proper exception handling throught the app
10 | Alert messages | If there is no response from server or if there is no Internet then user should get proper alert message and app shouldn't be crashed.

## Prepare App
IOS PROJECTS
Project Name: PrePare App
Current Developer: Ashish, Tushar
Sr. No | Modules | Tasks Details | Estimates | QA
1 | Dashboard | Need to check in all lower and higher resolutions devices. Especially Medicine Count (moving circle), Upcoming Appointment, etc.
2 | Calendar | User need to able to create new appointment from this screen. It needs to work properly.
3 | Notification | Need to implement badge functionality (popup number) while any new notification arrives. So it's need to popup as red color in app icon.
4 | Settings | Setting screen needs to work properly with all options except Report
5 | Reports | Waiting for further information from client | TBD
6 | Badges section | Waiting for further information from client | TBD
7 | Performance | App performance need to check, also check about Database storing process in locally.
8 | Layout issue | Layout need to check for all screens and need to make necessary improvements

## TOPCOD
IOS PROJECTS
Project Name: TOPCOD
Current Developer: Ashish, Tushar
Sr. No | Modules | Tasks Details | Estimates | QA
1
2
3
4
5
6
7

## ProPad
IOS PROJECTS
Project Name: ProPad
Current Developer: Vivek, Bhumesh
Sr. No | Modules | Tasks Details | Estimates | QA
1
2
3
4
5
6
7